## Phase Plan
FBC IMPLEMENTATION 2020
REQ NO | TASK DESCRIPTION | % Complete | QA DATE | PRIORITY | RESOURCE NAMES | COMMENTS
Cimas information provision
Preliminary Scheme information
| Benefit Guide | 0% | MONTH 1 |  | Cimas
| Premium Tables | 0% | MONTH 1 |  | Cimas
Full Scheme Information
| Benefit Guide | 0% | MONTH 1 |  | Cimas |  | 0% | 2019-12-18 | Cimas
| Scheme rules | 0% | MONTH 1 |  | Cimas |  | 0% | 2019-12-18 | Cimas
| Premium tables | 0% | MONTH 1 |  | Cimas |  | 0% | 2019-12-18 | Cimas
| Premium payer groupings | 0% | MONTH 1 |  | Cimas |  | 0% | 2019-12-18 | Cimas
| Scheme letterhead and logos | 0% | MONTH 1 |  | Cimas |  | 0% | 2019-12-18 | Cimas
| Administrator designation for comms | 0% | MONTH 1 |  | Cimas |  | 0% | 2019-12-18 | Cimas
| Administrator address | 0% | MONTH 1 |  | Cimas
| Scheme banking details for claims and contributions accounts - full listing | 0% | MONTH 1 |  | Cimas
| Client services Contact numbers | 0% | MONTH 1 |  | Cimas
| Client services Email addresses | 0% | MONTH 1 |  | Cimas
| Provide lettehead and Logos | 0% | MONTH 1 |  | Cimas
| Provide insurer web site url | 0% | MONTH 1 |  | Cimas
| Provide insurer Emergency numbers | 0% | MONTH 1 |  | Cimas
| Email server details (smtp) | 0% | MONTH 1 |  | Cimas
| Incoming mail (Imap) details | 0% | MONTH 1 |  | Cimas
Mobile App - Excluding Wellness
| DUNS number registration - pre-requisite for IOS account setup | 0% | MONTH 3 |  | Cimas
| Android Account Setup | 0% | MONTH 3 |  | Liana/Kelvin | Mobile Team to assist
| IOS Account Setup | 0% | MONTH 3 |  | Liana/Kelvin | Mobile Team to assist
| Default Andoid App setup per scheme | 0% | MONTH 3 |  | Mobile Team
| Default IOS App setup per scheme | 0% | MONTH 3 |  | Mobile Team
| Live Depoyment IOS | 0% | MONTH 3 |  | Apple
| Live Depoyment Android | 0% | MONTH 3 |  | Google
SMS
| Intergration Specs | 100% | N/A |  | Liana | Afrosoft - already integrated
| Third Party/Cimas to provide Login/connection strings | 0% | MONTH 2 |  | Afrosoft
| Intergration Setup | 0% | MONTH 2 |  | Delon
| Setup of connection strings | 0% | MONTH 2 |  | Delon
| Test with third party | 0% | MONTH 2 |  | Delon
| Firewall Setup | 0% | MONTH 2 |  | Sean A
Test Environment Setup
| Database setup | 0% | MONTH 1 |  | Siphiwe
| Config setup and checks | 0% | MONTH 1 |  | Asha
| BI Instance setup | 0% | MONTH 1 |  | Siyabonga
| Config setup and checks | 0% | MONTH 1 |  | Muriel
| Correspondence setup | 0% | MONTH 1 |  | Siphiwe
| Config setup and checks | 0% | MONTH 1 |  | Delon
| Provide document for local PC setup | 0% | MONTH 1 |  | Raymond/Sean
| Setup of Hip launcher for client | 0% | MONTH 1 |  | Cimas
| testing with client from 2cana offices to Cimas | 0% | MONTH 1 |  | brett/Kelvin
| Setup of VM | N/A | MONTH 1 |  | Liana
| Infrastructure setup | 0% | MONTH 1 |  | Raymond
| Correspondence engine |  |  | Brett
| Managed server created QA (include mobile) | 0% | MONTH 1 |  | Brett
| Managed server created LIVE (Include mobile) | 0% | MONTH 1 |  | Brett
| Create data source (QA) | 0% | MONTH 1 |  | Brett
| Create data source | 0% | MONTH 1 |  | Brett
| Install Application (QA) | 0% | MONTH 1 |  | Brett
| Install Application | 0% | MONTH 1 |  | Brett
| Folder tree structure (QA) | 0% | MONTH 1 |  | Brett/Andrew
| Folder tree structure | 0% | MONTH 1 |  | Brett/Andrew
| Database configuration entries (QA) | 0% | MONTH 1 |  | Brett
| Database configuration entries | 0% | MONTH 1 |  | Brett
| Printing |  |  |  | Brett
| Details of file server for storing the system generated files | 0% | MONTH 2 |  | cimas
| Create shares | 0% | MONTH 2 |  | Brett
| Print setup | 0% | MONTH 2 |  | Brett
| Test that printing go to the share | 0% | MONTH 2 |  | Cimas
| Emailing |  |  | N/A
| Email setup |  | MONTH 2 |  | Delon
| Incoming: |  | MONTH 2
| configure each mailbox | 0% | MONTH 2 |  | cimas
| Username and Login | 0% | MONTH 2 |  | cimas
| Setup Workflow routing | 0% | MONTH 2 |  | Delon
| Test technical setup for emailing | 0% | MONTH 2 |  | Delon
| Outgoing: |  | MONTH 2
| configure outgoing mailbox | 0% | MONTH 2 |  | cimas
| Username and Login | 0% | MONTH 2 |  | cimas
| Test technical setup for emailing on QA | 0% | MONTH 2 |  | Delon
| Duplicate settings to PROD | 0% | MONTH 2 |  | Delon
Setup
| Auth Types and Rules | 0% | MONTH 1 |  | Verena
| Benefit indicators | 0% | MONTH 1 |  | Verena
| Drugs | 0% | MONTH 1 |  | Verena
| Pricing Rules | 0% | MONTH 1 |  | Josh
| Providers/Networks | 0% | MONTH 1 |  | Verena
| Product Rules | 0% | MONTH 1 |  | Verena
Membership Rules
| Workflows | 0% | MONTH 1 |  | Asha
| Bank details Approval process | 0% | MONTH 1 |  | Tamryn
| Waiting period + underwriting setups | 0% | MONTH 1 |  | Josh/Asha
| document type setup | 0% | MONTH 1 |  | Brett/Asha
| domain tables setup | 0% | MONTH 1 |  | Asha
New Database Setup
| Client context cleanup on non-transactional data | 0% | MONTH 1 |  | Asha
Account setup
| Provide staff details | 0% | MONTH 1 |  | Cimas
| Provide Cimas format for different User Roles | 0% | MONTH 1 |  | Cimas
| Cimas to Map staff members to the roles | 0% | MONTH 1 |  | Cimas
| Update roles based on Cimas information provided | 0% | MONTH 1 |  | Verena
| Load staff details | 0% | MONTH 1 |  | Verena
| Review Staff setup | 0% | MONTH 1 |  | Kelvin/Cimas
| Adjust staff roles | 0% | MONTH 1 |  | Cimas
Auths and Templates
| Auth types setup | n/a | MONTH 1 |  | Asha/Josh
| Templates setup | N/A | MONTH 1 |  | Asha
Finance and Billing Rules
| Cimas to confirm Billing Rules (Advanced or arrears) | 0% | MONTH 1 |  | Cimas | For Joan
| Cimas to confirm Suspension Rules | 0% | MONTH 1 |  | Cimas | For Joan
| Special days setup | 0% | MONTH 1 |  | Cimas | Listing of public holidays
Correspondence
Correspondence engine setup
| Setup Configuration items | 0% | MONTH 1 |  | Brett
| Correspondence and template settings | 0% | MONTH 1 |  | Bukasa
| Setup Letterheads and Logos | 0% | MONTH 1 |  | Bukasa
| Standard SMS wording | 0% | MONTH 1 |  | Bukasa
| Client Document pack | 0% | MONTH 1 |  | Bukasa | Standard HIP letters - No changes required
| Standard HIP Letter wording sign-off | 0% | MONTH 1 |  | Cimas
| Standard HIP Email wording sign-off (Where letter is emailed) | 0% | MONTH 1 |  | Cimas
| Standard sms wording sign-off | 0% | MONTH 1 |  | Cimas
| Deploy letters etc to QA | 0% | MONTH 1 |  | Thrisha
| Deploy letters etc to Live | 0% | MONTH 1 |  | Thrisha
| Integration services/data | 0% | MONTH 1 |  | Thrisha
Setup Test Packs
| Claims Test Packs | 0% | MONTH 1 |  | Cimas | Full test packs across products/discplines/benefit areas etc
| Claims test pack that are associate to Auth test pack (Claims to Auths testing) | 0% | MONTH 1 |  | Cimas
| Membership test packs | 0% | MONTH 1 |  | Cimas | Product calculations - eg. Add/lapse/change product/change payer etc
| Finance test packs | 0% | MONTH 1 |  | Cimas
Department Setup
| Setup new departments and linking to workflows | 0% | MONTH 1 |  | Asha
Month end run Setup
| Statement run setup | 0% | AFTER GO-LIVE |  | Brett
| Review Monthend Run results/statements | 0% | AFTER GO-LIVE |  | Cimas
Membership card printing
| confirm if rawdata vs image file | 0% | MONTH 1 |  | Cimas | What images are we getting (format ie jpg) just for photos
| Required fields for what card requires | 0% | MONTH 1 |  | Cimas
| Sample card | 0% | MONTH 1 |  | Cimas
| Setup Card format - cater for member information on one side of card | 0% | MONTH 2 |  | Bukasa
| Generate Card file for test printing | 0% | MONTH 2 |  | Bukasa
| Print test card print data file for sign off | 0% | MONTH 2 |  | Cimas
| Card file sign off | 0% | MONTH 2 |  | Cimas
| Cimas to manually link photos on card if required | 0% | MONTH 2 |  | Cimas | This is at card print stage
Scanning
| Barcode label sizes | 0% | MONTH 1 |  | Cimas
| Confirm compatible scanner options in line with Cimass printing needs | 0% | MONTH 1 |  | Cimas
| Confirm desired specification of scanner based on options provided | 0% | MONTH 1 |  | Cimas
| Kodak/bartender Quotation | 0% | MONTH 1 |  | Liana
| Confirm Kodak/bartender Purchase | 0% | MONTH 1 |  | Cimas
| Purchase Kodak/bartender software | 0% | MONTH 1 |  | Cimas
| UPS for scanning PC | 0% | MONTH 1 |  | Cimas
| Installation of software and scanner setup | 0% | MONTH 2 |  | Brett/Nicholas
| Testing with client | 0% | MONTH 2 |  | Brett/Nicholas
BI Reports Setup
| Setup BI structures | 0% | MONTH 1 |  | Verena
| Setup Bi connectity to DB | 0% | MONTH 1 |  | Verena
| Setup Bi models | 0% | MONTH 1 |  | Verena
| Setup Standard HIP reports | 0% | MONTH 1 |  | Verena
| Fin DW Setup | 0% | MONTH 3 |  | Sean
Bank File Formats
| Provide EFT claims payment file formats | 0% | MONTH 1 |  | Cimas | Third party - called EFT
| Provide EFT collections file formats | 0% | MONTH 1 |  | Cimas | Third party - called EFT
| Develop Claims payment file format based on EFT specifications | 0% | MONTH 1 |  | Delon | Third party - called EFT
| Develop Collections file format based on EFT specifications | 0% | MONTH 1 |  | Delon | Third party - called EFT
| Test Claims payment format directly with Cimas and EFT | 0% | MONTH 1 |  | EFT/Cimas/Delon | Third party - called EFT
| Test Collections format directly with Cimas and EFT | 0% | MONTH 1 |  | EFT/Cimas/Delon | Third party - called EFT
| Sign off of EFT claims file format | 0% | MONTH 1 |  | Cimas
| Sign off of EFT contributions file format | 0% | MONTH 1 |  | Cimas
| Setup Production with EFT claims file format | 0% | MONTH 2 |  | Delon
| Setup Production with EFT contributions file format | 0% | MONTH 2 |  | Delon
Data Takeon
Membership data
Initial Iteration
| Receive formats | 0% | MONTH 1 |  | Tamryn
| Review Formats | 0% | MONTH 1 |  | Tamryn
| Receive Sample file | 0% | MONTH 1 |  | Tamryn
| Review Sample files | 0% | MONTH 1 |  | Tamryn
| Load Sample files | 0% | MONTH 1 |  | Tamryn
| Provide Feedback on File corrects/Data corrections for Members | 0% | MONTH 1 |  | Tamryn
| Provide Feedback on File corrects/Data corrections for payer | 0% | MONTH 1 |  | Tamryn
Second Iteration
| Corrections to be applied to Members file | 0% | MONTH 1 |  | Cimas | based on feed from Initial Iteration
| Corrections to be applied to Payers file | 0% | MONTH 1 |  | Cimas | based on feed from Initial Iteration
| Provide full member file | 0% | MONTH 1 |  | Cimas
| Provide full payer file | 0% | MONTH 1 |  | Cimas
| Load full member file in QA | 0% | MONTH 1 |  | Tamryn
| Load full payer file in QA | 0% | MONTH 1 |  | Tamryn
| Provide Feedback on File corrects/Data corrections for Members | 0% | MONTH 1 |  | Tamryn
| Provide Feedback on File corrects/Data corrections for payer | 0% | MONTH 1 |  | Tamryn
New Products
| Shortened product list to be provided | 0% | MONTH 1 |  | Cimas
| Require product and contribution values and structures | 0% | MONTH 1 |  | Cimas
| Provide Addon pricing and structures | 0% | MONTH 1 |  | Cimas
| Product mappings to be provided if required | 0% | MONTH 1 |  | Cimas
Critical + Dry Run Iteration
| New Product must be included in membership file |  | MONTH 1 |  |  | Please ensure members are mapped to the new product prior to sending this file
| Corrections to be applied to Members file | 0% | MONTH 1 |  | Cimas
| Corrections to be applied to Payers file | 0% | MONTH 1 |  | Cimas
| Provide full member file | 0% | MONTH 1 |  | Cimas
| Provide full payer file | 0% | MONTH 1 |  | Cimas
| Load full member file in QA | 0% | MONTH 1 |  | Tamryn
| Load full payer file in QA | 0% | MONTH 1 |  | Tamryn
| Provide Feedback on File corrects/Data corrections for Members | 0% | MONTH 1 |  | Tamryn
| Provide Feedback on File corrects/Data corrections for payer | 0% | MONTH 1 |  | Tamryn
Billing Runs QA
| Turn on Billing Runs on QA | 0% | MONTH 1 |  | Joan
| Test Billing Runs on QA | 0% | MONTH 1 |  | Cimas
| Old System - Membership Freeze for 14 Feb 20 (no more changes on the old system) | 0% | MONTH 2 |  | Cimas | If changes required, Busines process to double capture on both systems.
Final Iteration
| Corrections to be applied to Members file | 0% | MONTH 2 |  | Cimas
| Corrections to be applied to Payers file | 0% | MONTH 2 |  | Cimas
| Provide full member file | 0% | MONTH 2 |  | Cimas
| Provide full payer file | 0% | MONTH 2 |  | Cimas
| Load full member file in PROD | 0% | MONTH 2 |  | Tamryn
| Load full payer file in PROD | 0% | MONTH 2 |  | Tamryn
| Premium validations | 0% | MONTH 2 |  | Tamryn
Membership & Billing Sign off
| Review membership Data | 0% | MONTH 3 |  | Cimas
| Review membership contribution calculations correct per product | 0% | MONTH 3 |  | Cimas
| Review payer pro forma balances | 0% | MONTH 3 |  | Cimas
| If Required, correct on HIP, membership details/products etc | 0% | MONTH 3 |  | Cimas
| Sign off membership | 0% | MONTH 3 |  | Cimas
| Sign off Payers | 0% | MONTH 3 |  | Cimas
Billing Balances
| Provide Billing balances - for Production opening balances | 0% | MONTH 2 |  | Cimas | Member and Payer contribution balances
| Load balances on production where given entity | 0% | MONTH 3 |  | Tamryn
| If All looks correct then load manual journal to set balance to required balance | 0% | MONTH 3 |  | Cimas
| Monthly billing + oustanding balances sign off + User proforma reports | 0% | MONTH 3 |  | Cimas
Billing Runs Prod
| Setup PROD Billing Run Dates | 0% | MONTH 1 |  | Joan
| Turn on Billing Runs on PROD | 0% | MONTH 1 |  | Joan
| Run Billing on PROD | 0% | MONTH 3 |  | Cimas
| DO NOT RELEASE STATEMENTS - REVIEW | 0% | MONTH 3 |  | Cimas
| Review and Sign off - Billing balances and Statements | 0% | MONTH 3 |  | Cimas
| Release Billing statements | 0% | MONTH 3 |  | Cimas
| Waiting Periods to benefit mappings file (Which tariff codes constitue the exclusion) | 0% | MONTH 1 |  | Josh/Asha
| Exclusions to benefit mappings file (Which tariff codes constitue the exclusion) | 0% | MONTH 1 |  | Josh/Asha
Web Portals
| Cimas Branding | 0% | MONTH 3 |  | Thrisha
| Registration to be done via email and SMS | 0% | MONTH 3 |  | Thrisha
| Member portal changes - simplify | 0% | MONTH 3 |  | Thrisha
| Member - QA | 0% | MONTH 3 |  | Thrisha
| Sign off Member | 0% | MONTH 3 |  | cimas
| Employer portal changes - simplify | 0% | MONTH 3 |  | Thrisha
| Employer - QA | 0% | MONTH 3 |  | Thrisha
| Sign off - Employer | 0% | MONTH 3 |  | cimas
| Provider portal changes - simplify | 0% | MONTH 3 |  | Thrisha
| Provider - QA | 0% | MONTH 3 |  | Thrisha
| Sign off - Provider | 0% | MONTH 3 |  | cimas
| Deploy member to QA | 0% |  |  | Thrisha
| Deploy employer to QA | 0% |  |  | Thrisha
| Deploy Provider to QA | 0% |  |  | Thrisha
| Provide Member URL to cimas | 0% |  |  | Thrisha
| Provide Employer URL to cimas | 0% |  |  | Thrisha
| Provide Provider URL to cimas | 0% |  |  | Thrisha
| Member portal Link setup on website | 0% |  |  | cimas
| Employer portal Link setup on website | 0% |  |  | cimas
| Provider portal Link setup on website | 0% |  |  | cimas
Claims/Benefit Setup
| Provide new Tariff list/desciption/benefit mapping and pricing | 0% |  |  | Cimas
| Provide new drug database, description/pricing | 0% |  |  | Cimas
| Setup the 6(ish) new products + insurers | 0% |  |  | Nishen
| Setup new Products design for 2020 | 0% |  |  | Nishen/Rules team
| Benefit Refresh - QA | 0% |  |  | Nishen
| Claims Testing based on Test pack | 0% |  |  | Cimas
| Claims Test pack sign off all products | 0% |  |  | Cimas
| Benefit Refresh - Prod | 0% |  |  | Nishen
Providers
| New BHF provider listing - Full data file listing | 0% |  |  | Cimas
| BHF provider number mappings vs old Afhoz number | 0% |  |  | Cimas
| Provide Provider Banking details | 0% |  |  | Cimas
| Load new BHF provider file QA | 0% |  |  | Asha
| Load new BHF provider file - banking details QA | 0% |  |  | Asha
| Provide new BHF provider file for PROD | 0% |  |  | Cimas
| Provide new provider file - banking details PROD | 0% |  |  | Cimas
| Load new BHF provider file PROD | 0% |  |  | Asha
| Load new BHF provider file - banking details PROD | 0% |  |  | Asha
| Training |  |  |  |  | Proposed
| Workflow training | 0% |  |  | Kelvin/Bruce/Gerda
| Membership Training | 0% |  |  | Kelvin/Bruce/Gerda
| Authorisation Training | 0% |  |  | Kelvin/Bruce/Gerda
| Claims training | 0% |  |  | Kelvin/Bruce/Gerda
| Finance/Billing Training | 0% |  |  | Kelvin/Bruce/Gerda
| Business Intelligence / Reports usage Training | 0% |  |  | Kelvin/Bruce/Gerda
| Portal Training | 0% |  |  | Kelvin/Bruce/Gerda
Suspension Run
| Turn on Automatic suspension in QA | 0% |  |  | Joan
| Configure and set Rules for Suspension runs | 0% |  |  | Joan
| Test Automatic suspensions in QA | 0% |  |  | Cimas
| Sign off suspension Processs - QA | 0% |  |  | Cimas
| Turn on Automatic suspension in PROD | 0% |  |  | Joan
| Run first suspension Run | 0% |  |  | Cimas
| Cimas to review and sign off Suspend members letters/amounts on PROD | 0% |  |  | Cimas
| Release Suspension Communication | 0% |  |  | Cimas
Health 263 Integration
QA
| Test Card holder file - Standard HIP format (utilised by Health263) | 0% |  |  | 2Cana
| Health263 review and provide feedback | 0% |  |  | Health263
| Setup Networking | 0% |  |  | Health263/2Cana
| Realtime integration services - test | 0% |  |  | Health263/2Cana
| Test Realtime claims submission | 0% |  |  | Health263
| Business to test realtime intregration of claims and Adjudication | 0% |  |  | Cimas
| Sign off Claims process (realtime integration) | 0% |  |  | Cimas
PROD
| Cardholder activation - release of daily files to Health 263 | 0% |  |  | 2Cana
| Real time claims activation | 0% |  |  | 2Cana
| Backlog claims submission | 0% |  |  | Health263 | Health263 needs to ensure provider/tariff/drugs codes are already mapped into the new format - 8am
Claim Payment Run
QA
| Setup claims in QA for payment run testing | 0% |  |  | Cimas
| Setup Claim payment run on QA | 0% |  |  | Brett
| Provide Provider Claims Aged Balances | 0% |  |  | Cimas | Mapped to new provider numbers
| Load Provider Claims Aged Balances | 0% |  |  | Joan
| Provide Member Claims Aged Balances | 0% |  |  | Cimas
| Load Member Claims Aged Balances | 0% |  |  | Joan
| Setup ACB payment process on QA | 0% |  |  | Joan/Brett
| Run claims payment run in QA | 0% |  |  | Cimas
PROD
| Setup Claim payment run on PROD | 0% |  |  | Brett
| Provide Provder Claims Aged Balances | 0% |  |  | Cimas | Mapped to new provider numbers
| Load Provider Claims Aged Balances | 0% |  |  | Joan
| Provide Member Claims Aged Balances | 0% |  |  | Cimas
| Load Member Claims Aged Balances | 0% |  |  | Joan
| ACB payment process on PROD | 0% |  |  | Joan/Brett
| RUN first claims payment run | 0% |  |  | Cimas
| Online Portal - Onboarding members |  |  |  |  | Only for onboarding members - not separate product/dependant changes etc
Direct Sales team Portal
| List of previous schemes | 0% |  |  | Cimas
| Provide copy of latest membership application form | 0% |  |  | Cimas
| List of Medical questions (same as application form) | 0% |  |  | Cimas | Match standard membership application form
| Setup single direct sales (broker entry - 0% commission) | 0% |  |  | 2Cana
| Setup direct sales portal | 0% |  |  | 2Cana
QA
| Test capture of Online application | 0% |  |  | Cimas
| Sign off process | 0% |  |  | Cimas
Prod
| Activate Live Portal on production | 0% |  |  | 2Cana
| Provide Cimas with URL for setup on their internal system | 0% |  |  | Cimas

## Summary
Receive scheme information from Cimas | 2019-11-21
Receive Test packs from Cimas | 2020-01-02
Infrastructure setup | December 2019
Test Environment setup | December 2019
Correspondence engine | December 2019
Printing | March 2020
emailing | February 2020
Setup standard HIP correspondence | March 2020
Static History Portal on QA | 2020-03-01
Static History Portal on Live | 2020-04-01
SMS setup | January 2020
Member mobile App on QA | 2020-03-01
Member mobile App Live | 2020-04-01
benefits | February 2020
tariffs | February 2020
Rates | February 2020
CPT codes | February 2020
Special Development
CPT codes instead of tariff codes | February 2020
BHF instead of AFHOZ | February 2020
Load Membership on QA | January 2020
Load Membership on Live | March 2020
Verfication of System Processes | March 2020
Portals | March 2020
Training | 1-mar-20 to 14-mar-20
System Freeze for 2 weeks | 14-mar-20 to 1-apr-20
Go Live with membership | 2020-04-01

## Risks
Risk Log
Ref No | Description of Risk | Date Logged | Raised By | Likelihood | VLOOKUP likelihood | Impact | VLOOKUP Impact | Risk Rating | Actions to Mitigate (Resp) | Date Closed | Current status
|  |  |  | Likelihood |  | Impact
|  |  |  | Rare | 1 | Insignificant | 1 | (Can result in an insignificant business disruption and/or an immaterial financial loss)
|  |  |  | Unlikely | 2 | Minor | 2 | (Can result in a minor business disruption and/or a small financial loss)
|  |  |  | Possible | 3 | Moderate | 3 | (Can result in a moderate business disruption and/or a material financial loss)
|  |  |  | Likely | 4 | Major | 4 | (Can result in a major business disruption and/or a significant financial loss)
|  |  |  | Almost Certain | 5 | Catastrophic | 5 | (Can result in the closure/failure of the business unit)

## Go-Live Date
Project Plan Go-Live Date
Ref No | Go-Live Date | Reason for Change | Communicated
1 | 2001-04-20
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18

## Incident log
Incident Log
Number | Date | Incident | Impact | Reason / Explanation | Resolution | Prevention / Lesson Learnt | Responsible Team | Status | Ongoing Activity | BA

## Outstanding Requirements
Outstanding Requirements
Number | Requirement | Description | Date Logged | Person Responsible (If known) | Comments | Deadline date | Revised Deadline date | Status
outstanding
outstanding
outstanding
complete
complete
complete
complete
outstanding
complete
complete
complete
outstanding
outstanding
outstanding
outstanding
outstanding
outstanding

## Scope Change
Scope Change Log
Item No | Description | Reason for change | Requested by | Date requested on | Developer | Status | Estimate
[5 empty] | Estimate |  | Estimate
1
[6 empty] | TOTAL | 0

## Decisions
Decisions Log
Ref No | Decision | Date Logged | Driver | Comments/Notes
1
2
3
4

## Infrastructure Setup (hidden)
Infrastructure setup
| Finalise solution | 0% |  | Kelvin
| Backup link | 0% |  | Kelvin
Setup for Parallel run
| Connectivity between Teraco Isando/Malawi Pretoria/2cana Durban | 0% |  | Kelvin
| Install and configure networking equipment at Teraco | 0% |  | Kelvin
| Setup Site to Site VPN | 0% |  | Kelvin
| Confirm required environments - confirmed as QA and PROD only due to licencing concerns | 0%
| Hosting at Teraco | 0% |  | Kelvin
34862 | Install ODA AT Teraco | 0% |  | Andrew
34862 | Configure ODA post installation | 0% |  | Andrew
34862 | Setup of VMs on ODA |  |  | Andrew
34862 | Copy VMS's to ODA
34862 | Forms | 0% |  | Andrew
34862 | BIP | 0% |  | Andrew
34862 | JAVA | 0% |  | Andrew
34862 | Support/Jump box | 0% |  | Andrew
34862 | Configure and Startup VM's on ODA
34862 | Forms | 0% |  | Andrew
34862 | BIP | 0% |  | Andrew
34862 | JAVA | 0% |  | Andrew
34862 | Support/Jump box | 0% |  | Andrew
34862 | Setup Databases
34862 | Setup QA DB | 0%
34862 | Create DB | 0% |  | Siphiwe
34862 | Export BestPOC to QA | 0% |  | Siphiwe
34862 | Setup PROD DB | 0%
34862 | Create DB | 0% |  | Siphiwe
34862 | Export data from BestQA to PROD | 0% |  | Siphiwe
34862 | Setup database users | 0% |  | Joan
34862 | Refine firewall settings | 0% |  | Neville
34862 | Test connectivity | 0% |  | Andrew/Neville
Managed server setup
34862 | Mediscor | 0% |  | Siphiwe
34862 | Mediswitch | 0% |  | Siphiwe
34862 | Correspondence Engine | 0%
34862 | Docviewer | 0% |  | Siphiwe
34862 | BIP | 0% |  | Siphiwe
34862 | Email IN | 0% |  | Siphiwe
34862 | Email OUT | 0% |  | Siphiwe
34862 | Bounced email handling | 0% |  | Siphiwe
34862 | ERA's | 0% |  | Siphiwe
34862 | SMS | 0% |  | Siphiwe
34862 | Portals | 0% |  | Siphiwe
34862 | Firewall configuration to allow Apex ports | 0% |  | Neville
34862 | Install Applications on Weblogic Server
34862 | Correspondence Engine | 0% |  | Siphiwe
34862 | Transfer Engine | 0% |  | Siphiwe
34862 | Mediscor | 0% |  | Siphiwe
34862 | Mediswitch | 0% |  | Siphiwe
34862 | Portals | 0% |  | Siphiwe
Correspondence Engine configuration ( BESTQA)
34862 | Docviewer - config | 0% |  | Brett
34862 | BIP - Config | 0% |  | Brett
34862 | Outgoing email
34862 | Email setup | 0% |  | Brett
34862 | Email Setup for processes (bins) | 0% |  | Brett
34862 | Test technical setup for emailing | 0% |  | Brett
34862 | Incoming Email
34862 | Email setup | 0% |  | Brett
34862 | Email Setup for processes (bins) | 0% |  | Brett
34862 | Test technical setup for emailing | 0% |  | Brett
34862 | bounced email handling
34862 | Email setup | 0% |  | Brett
34862 | Email Setup for processes (bins) | 0% |  | Brett
34862 | Test technical setup for emailing | 0% |  | Brett
34862 | Printing
34862 | Folder and share to be setup to place print files | 0% |  | Andrew
34862 | Details of interaction with print house | 0% |  | Kelvin
34862 | Integration with Print house | 0% |  | Brett
34862 | Print setup | 0% |  | Brett
34862 | Test printing process | 0% |  | Brett
34862 | SMS | 0% |  | Brett
Install New ODAS's
| - Preparation of Diagramatic representation of final solution/various environments : Peter – 18 Jan | 0% |  | Peter
| - Andrew to provide configs to Luige for address/naming convention confirmation – 18 Jan | 0% |  | Andrew
| Site Audit | 0% |  | DBA
| Site Audit | 0% |  | DBA
| - Arrange further racking space/Infrastructure requirements as per site audit : Luige – TBC | 0% |  | Kelvin
| - Andrew to provide PIeTER WITH oda CONFIG. | 0% |  | Andrew
- Teraco:
| o Delivery of ODA to Teraco installation site : Axiz – 3 days (2 days notice and delivery on 3rd day) | 0% |  | Ridwan
| o Creation of DNS host names - Luige | 0% |  | Kelvin
| o Racking of ODA : Oracle/Pieter – 1 day | 0% |  | DBA
| § Day one: | 0% |  | DBA
| INFORMATION: EIS Checklist Steps & Estimated Timing | 0% |  | DBA
| Item First Page Est. Duration | 0% |  | DBA
| Preparation 4 hours | 0% |  | DBA
| Unpacking 30 mins | 0% |  | DBA
| Assembly / Cabling 1.5 Hours | 0% |  | DBA
| ILOM Service Processor Configuration 30 mins | 0% |  | DBA
| Server Power On & POST 20 mins | 0% |  | DBA
| o ODA Software configuration : Oracle/Pieter – 2 days | 0% |  | DBA
| § Day two and three: | 0% |  | DBA
| Instructions for Virtualized ODA (This will be done on BOTH NODES) | 0% |  | DBA
| Updating Firmware Components | 0% |  | DBA
| Deploying ODA_BASE | 0% |  | DBA
| Install patches | 0% |  | DBA
| “Custom” Configuration | 0% |  | DBA
| Post Validation | 0% |  | DBA
| Common to both Bare Metal & Virtualized ODA | 0% |  | DBA
| Securing the ILOM Service Processors (SP) | 0% |  | DBA
| Check Storage expansion | 0% |  | DBA
| o Network checks/configuration, VM and Database Migrations : Siphiwe/Andrew – 5 days: | 0%
| § Network: | 0%
| · Let Luige know of network requirements - Andrew | 0% |  | Andrew
| · Check DMZ - Andrew/Luige | 0% |  | Andrew
| § DB Migration - Siphiwe | 0% |  | Siphiwe
| · Create DB | 0% |  | Siphiwe
| · Transfer data – 1 day downtime required for this – Potential to use NFS share to get this done. Siphiwe will investigate | 0% |  | Siphiwe
| · Reconfigure backups | 0% |  | Siphiwe
| § VM Migration - Andrew | 0% |  | Andrew
| · Create repository | 0% |  | Andrew
| · Export VMS from x5 – to be scheduled for evening/night | 0% |  | Andrew
| · Import to x6 | 0% |  | Andrew
| · Reconfigure VMs e.g scan setup | 0% |  | Andrew
| § Checking – Apps team | 0% |  | Apps Team
| § Document migration – Andrew | 0% |  | Andrew
| § CLOUDFS migration - Andrew | 0% |  | Andrew
| o Allowance for post migration checks and resolution of issues : All teams – 2 days | 0% |  | All teams
- Faerie Glen:
| o Delivery of ODA to Faerie Glen installation site : Axiz – 3 days (2 days notice and delivery on 3rd day) | 0% |  | Chanice
| o Racking of ODA : Oracle/Pieter – 1 day | 0% |  | DBA
| § Day one: | 0% |  | DBA
| INFORMATION: EIS Checklist Steps & Estimated Timing | 0% |  | DBA
| Item First Page Est. Duration | 0% |  | DBA
| Preparation 4 hours | 0% |  | DBA
| Unpacking 30 mins | 0% |  | DBA
| Assembly / Cabling 1.5 Hours | 0% |  | DBA
| ILOM Service Processor Configuration 30 mins | 0% |  | DBA
| Server Power On & POST 20 mins | 0% |  | DBA
| o ODA Software configuration : Oracle/Pieter – 2 days | 0% |  | DBA
| § Day two and three: | 0% |  | DBA
| Instructions for Virtualized ODA (This will be done on BOTH NODES) | 0% |  | DBA
| Updating Firmware Components | 0% |  | DBA
| Deploying ODA_BASE | 0% |  | DBA
| Install patches | 0% |  | DBA
| “Custom” Configuration | 0% |  | DBA
| Post Validation | 0% |  | DBA
| Common to both Bare Metal & Virtualized ODA | 0% |  | DBA
| Securing the ILOM Service Processors (SP) | 0% |  | DBA
| Check Storage expansion | 0% |  | DBA
| o Network checks/configuration, VM and Database Migrations : Siphiwe/Andrew – 5 days | 0% |  | Andrew/Siphiwe
| o Allowance for post migration checks and resolution of issues : All teams – 2 days | 0% |  | All teams
BI SETUP
34862 | Setup of VMs on ODA |  |  | Andrew
34862 | Copy VMS's to ODA
34862 | Forms | 0% |  | Andrew
34862 | BIP | 0% |  | Andrew
34862 | JAVA | 0% |  | Andrew
34862 | Support/Jump box | 0% |  | Andrew
34862 | Configure and Startup VM's on ODA
34862 | Forms | 0% |  | Andrew
34862 | BIP | 0% |  | Andrew
34862 | JAVA | 0% |  | Andrew
34862 | Support/Jump box | 0% |  | Andrew
34862 | Setup Databases
34862 | Setup PROD DB | 0%
34862 | Create DB | 0% |  | Siphiwe
34862 | Export data from QA to PROD | 0% |  | Siphiwe
34862 | Setup database users | 0% |  | Joan
34862 | Refine firewall settings | 0% |  | Neville
34862 | Test connectivity | 0% |  | Andrew/Neville
Managed server setup
34862 | Mediscor | 0% |  | Siphiwe
34862 | Mediswitch | 0% |  | Siphiwe
34862 | Correspondence Engine | 0%
34862 | Docviewer | 0% |  | Siphiwe
34862 | BIP | 0% |  | Siphiwe
34862 | Email IN | 0% |  | Siphiwe
34862 | Email OUT | 0% |  | Siphiwe
34862 | Bounced email handling | 0% |  | Siphiwe
34862 | ERA's | 0% |  | Siphiwe
34862 | SMS | 0% |  | Siphiwe
34862 | Portals | 0% |  | Siphiwe
34862 | Firewall configuration to allow Apex ports | 0% |  | Neville
34862 | Install Applications on Weblogic Server
34862 | Correspondence Engine | 0% |  | Siphiwe
34862 | Transfer Engine | 0% |  | Siphiwe
34862 | Mediscor | 0% |  | Siphiwe
34862 | Mediswitch | 0% |  | Siphiwe
34862 | Portals | 0% |  | Siphiwe
34862 | Correspondence Engine configuration (PROD)
34862 | Docviewer - config | 0% |  | Brett
34862 | BIP - Config | 0% |  | Brett
34862 | Outgoing email
34862 | Email setup | 0% |  | Brett
34862 | Email Setup for processes (bins) | 0% |  | Brett
34862 | Test technical setup for emailing | 0% |  | Brett
34862 | Incoming Email
34862 | Email setup | 0% |  | Brett
34862 | Email Setup for processes (bins) | 0% |  | Brett
34862 | Test technical setup for emailing | 0% |  | Brett
34862 | bounced email handling
34862 | Email setup | 0% |  | Brett
34862 | Email Setup for processes (bins) | 0% |  | Brett
34862 | Test technical setup for emailing | 0% |  | Brett
34862 | Printing
34862 | Folder and share to be setup to place print files | 0% |  | Andrew
34862 | Details of interaction with print house | 0% |  | Kelvin
34862 | Integration with Print house | 0% |  | Brett
34862 | Print setup | 0% |  | Brett
34862 | Test printing process | 0% |  | Brett
34862 | SMS | 0% |  | Brett
Secure backups
Admin Server
34862 | Create VM | 0% |  | Andrew
34862 | Copy onto ODA | 0% |  | Andrew
34862 | Change IP address and configure DNS | 0% |  | Andrew/Kelvin
34862 | Install SB software | 0% |  | Andrew
Media Server
34862 | Create VM | 0% |  | Andrew
34862 | Copy onto ODA | 0% |  | Andrew
34862 | Change IP address and configure DNS | 0% |  | Andrew/Kelvin
34862 | Allocate NFS storage | 0% |  | Andrew/Kelvin
34862 | Install SB software | 0% |  | Andrew
Configure Secure Backup
34862 | Media config | 0% |  | Andrew
34862 | Host config | 0% |  | Andrew
34862 | Backup schedules | 0% |  | Andrew
Client installs
34862 | Identify clients | 0% |  | Andrew/Peter
34862 | Install secure backup client | 0% |  | Andrew
34862 | Add host to secure backup | 0% |  | Andrew
34862 | Add client file systems to data sets | 0% |  | Andrew
34862 | Test and implement | 0% |  | Andrew
Active Directory
34862 | Setup AD | 0%
34862 | Install Product | 0%
34862 | Apply to Best qa | 0%
34862 | Configure necessary components | 0%
34862 | Consider CRM logins | 0%
Desktop Setup
34862 | Provide Malawi with desktop setup document | 100% | 2018-07-06 | Raymond
34862 | Malawi to setup all desktops based on above document | 0% |  | Kelvin